## Priorities & Deliverables
Key
Complete
On track (will be achieved within timescale)
At risk (may not be achieved within timescale)
Off track (will not be achieved within timescale)
Not yet started
|  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Key Deliverables | Description of Planned Deliverables | Actions/ Outputs/Milestones | Action Owner | Status | Actions/ Outputs/Milestones | Action Owner | Status | Actions/ Outputs/Milestones | Action Owner | Status | Actions/ Outputs/Milestones | Action Owner | Status
Patient Engagement & Involvement | Ensure membership includes a minimum of two patient reps to support coproduction. Patient involvment with associated workplan activities will be co-ordinated through the AHP Lead (TP) and/or CAG Lead (TL) with oversight from the TVCA patient englagement lead. | Patient reps to be re confirmed (including soft tissue) ?TVCA still involved | CNS Teams | [8 empty] | LC
Operational Performance | TVCA Dashboard: All Trusts to have access to live tumour specific dashboard
Audit Trusts that have completed MDT streamlining and share best practice across the system via share and learns
| Review referral pathway | Address inconsistency of referral pathways - Primary Care not being aware of the referral pathway route i.e., not knowing where to refer into, identifying tumours and referring into the correct tumour site. TWR 2 week referrals need to be referred into radiology. Draft SOP with guidelines for the referal pathway to define that patients needs to be referred to sarcoma and only refer to sarcoma MDT when there is a sacroma identified. Website to be amended/ updated with accurate and clear information regarding referral. Referral forms to be reviewed and updated. |  |  |  | SP
Education & Workforce Development | Work with CAG lead, head of service improvement and primary care lead to establish and deliver training and development requirements that support service and patient experience improvement in FDS and EDI. | Initiate discussions around TVCA Primary Care Prevention and Detection Group. | HB-W | [8 empty] | CP
Locally Driven Programme | Embed sarcoma genomics in routine care | * Review the genomic testing pathway and plan efficiently due to the increasing number of referrals * Invite nurses to the G tab distribution list. * Commence discussion around the WGS Project * Send SP an updated list of identified patients Establish EPR request for the gemini blood test | SP
| Ensure quality & equitable care provision to all sarcoma patients within the Thames Valley Region. | Work with patient reps to consider/ define potential activities around quality & equitable care provision | All
| Ensure age appropriate facilitites at the NOC for patients undergoing surgery |  | All
| Follow up Sarcoma CNS annual report |  | N/a
| Succession Planning | Review the following areas: Pathology, Clinical Oncology and Surgery | N/a
Research & Development | Increase research recruitment: Have a research champion at each MDT to highlight if a patient is likely to be eligible for a trial. | Share information about ongoing, upcoming and closed research studies with MDT research nurses to help drive research recruitment, Volunteer/ Nominate a member from each MDT to be aware of trials and identify patients who might be eligible * Ensure numbers are correctly reported | TL, All
Pathways | to continue to review and amend all sarcoma pathways, ensuring guidelines are compliant with the sarcoma service specification: • Soft tissue limb and trunk • Skin • Retroperitoneal • Breast • Urology • Paediatric | Review pathways prion to March 2026 SAG for discussion at meeting. Ensure visible on website with dates/version numbers
Guidelines | To review and update all SAG guidelines which have expired/nearing expiry • Patient Management Policy • Hospital Referral Guidelines • Staging and Follow Up Guidelines – including PIFU | Review guidelines prion to March 2026 SAG for discussion at meeting. Ensure visible on website with dates/version numbers
Audits | To carry out SAG-wide audits, including against agreed pathways as per the requirements of the sarcoma service specification | to discuss at March SAG
Data | To monitor core datasets and data provision across the SAG, including: • Cancer Waiting Times • Cancer Outcomes and Services Dataset • COREPLUS5 - % of cases diagnosed at stage 1/2
Publication of patient outcomes | to review and monitor patient outcomes data
Genomics | to agree a SAG-wide policy on genomic testing in line with the sarcoma and paediatric service specifications • ensure a consistent approach across the region and feed into national discussions • collect and analyse available data
Patient Experience | To review and act on findings of the National Cancer Patient Experience Survey across the network • To obtain patient feedback via SAG patient representatives and patient feedback events
Trials | to ensure access to appropriate clinical studies. Ensure trial portfolio is consistent with available trials; that recruitment is maintained. Review trial portfolio and recruitment at SAG
Local Sarcoma Diagnostic clinics | To support all local diagnostic services to meet the requirements of the SAG’s diagnostic pathway document • To explore the addition of further diagnostic services within the region